## Sheet1
2013 Priorities
|  | Complete | No-action | Reasons
Item
Road Improvements |  | x
Bathrooms |  |  | x | Undefined problem
Kitchen |  |  | x | Possible cost, compliance with health board problems
Range Drainage |  | x
Range Berms |  | x
200 Yd range Widening |  | x
Rifle Pavillion Extension |  | x
Complete' Indoor Range
| Ventilation |  |  | Approx cost $25k ventilation project,
| Lighting |  |  | pending, est. $2000
| Target Area |  |  | lead mined, kickplates replaced
Skeet House & Sheds |  |  |  | Skeeet houses stained, 1 rifle range shed removed, 1 remains
Acquire Property |  |  | x | N/A
Roof |  | x |  | inspected, minor work done
Office Safe/storage |  |  |  | Junk reduced, stoage room built, container solution pending
Port-a-Potty |  |  |  | As needed
Archery Range |  | x
Clean Up Broken Clays |  | x
Larger Classroom Windows |  |  | x | No action taken
Scholarship |  |  | x | No action taken
Investment Account |  | x
Move Birds/Storage |  | x
Fire Pit By Archery Range |  |  | x
Exterior Work |  | x |  | New door, improved access, siding repaired
SomePossible Projects
Storage Room floor safety
Additional Classroom(s)
Store Room Weatherization
Indoor range floor/wall range
Stain new range construction
Timber clearing
Rifle range 'eyebrows'
Kitchen upgrade to code